## Sheet1
Sr No | Lesson | Question | Options | Answer | Explanation
1 | 2 | During a planning meeting, the project manager facilitated a discussion on the resource assignments of risk activities. By the end of the meeting, all risk activities had been assigned an owner. What risk management process is the project currently in? | A. Risk Management Planning | 1 | The risk management plan includes the documentation of risk-related roles and responsibilities. This involves a description of the roles (similar to a job description) and the assignment of risk activities. This is often confused with the assignment of risk ownership, which is done during the Risk Response Planning process and refers to the assignment of identified risks, not risk activities.
|  |  | B. Risk Identification | 0
|  |  | C. Risk Response Planning | 0
|  |  | D. Risk Monitoring and Control | 0
2 | 2 | The first major output of risk management is: | A. Risk register | 0
|  |  | B. Risk management plan | 1 | The first major output occurs within the Risk Management Planning process (also the first risk management process): the risk management plan. The risk management plan is essential to carrying out the other risk management process, including the creation of the risk register, which occurs within the second process
|  |  | C. Risk probability and impact matrix | 0
|  |  | D. Project management plan | 0
3 | 2 | All of the following are used as inputs in the creation of the risk management plan EXCEPT: | A. Cost management plan | 0
|  |  | B. Project acceptance criteria | 0
|  |  | C. Archived list of identified risks | 0
|  |  | D. Current list of identified risks | 1 | options A, B, and C are all items that are used through the list of process inputs within the Risk Management Planning process. Option D, however, has not been created at this point and can therefore not be used as an input. For clarification, the cost management plan is obtained as part of the project management plan; the project acceptance criteria is obtained through the project scope statement; and the archived list of identified risks comes from the organizational process assets.
4 | 2 | You are in the process of creating the risk management plan. To date, you and your team have established the approach, time and budget for conducting risk activities, as well as defined stakeholder risk tolerance levels. What critical item remains to be defined? | A. Risk management methodology | 0
|  |  | B. Risk probability and impact | 1 | A risk probability and impact definition is an important part of the risk management plan. Without these items properly defined, risks may be assessed inaccurately and inconsistently. Although option C was another possible choice, option B is considered to be more critical. According to the scenario, options A and D have already been taken care of.
|  |  | C. Risk categories | 0
|  |  | D. Budget | 0
5 | 2 | Which of the following BEST describes the purpose of planning meetings and analysis? | A. To define stakeholder risk tolerance levels | 0
|  |  | B. To define risk probability and impact | 0
|  |  | C. To assign risk-related roles and responsibilities | 0
|  |  | D. To generate the risk management plan | 1 | this can be a tricky question, since the planning meetings and analysis tool and technique is responsible for all of the items listed as options. However, the purpose is to generate the risk management plan, which will summarize the results of options A, B, and C.
6 | 2 | You are the risk manager of a $50,000,000 project. You have only been a part of the team for one week and already the varying priorities of the stakeholders are evident. Everyone seems to have a different opinion about risk. After updating stakeholder risk tolerance levels, what should the risk manager be MOST concerned with? | A. Assigning ownership of risk activities | 0
|  |  | B. Defining stakeholder risk attitudes | 0
|  |  | C. Defining risk probability and impact | 1 | in all cases it is important to define stakeholder risk tolerance levels and to properly define and document risk probability and impact. According to the scenario, stakeholder risk tolerance levels have already been documented. Although option B is an appealing choice, stakeholder risk attitudes should have been documented along with the risk tolerance levels, since the risk attitudes and risk tolerance levels are intertwined. That leaves option C, defining risk probability and impact. This will be critical to an accurate assessment of risks, particularly when stakeholders have varying priorities and agendas.
|  |  | D. Identifying the project risks | 0
7 | 2 | The risk probability and impact matrix can BEST be described as: | A. A look up table that combines probability and impact | 1 | Options B and C refer to risk probability and impact assessment, which uses the definitions of risk probability and impact documented within the risk management plan. Option A offers the best definition of the risk probability and impact matrix, which aims at assigning an overall risk by combining risk probability and impact.
|  |  | B. The definition of risk probability and impact | 0
|  |  | C. A means of assigning a risk probability rating | 0
|  |  | D. A visual representation of risk definitions | 0
8 | 2 | Risk management efforts typically begin at which stage of a project? | A. Prior to the start of the project | 0
|  |  | B. Initiating phase | 1 | risk management efforts should begin as early as the start of the project. This would rule out all options except for B, the initiating phase. This should not be confused with the completion of the risk management plan, which should occur early on within the planning process group
|  |  | C. Planning phase | 0
|  |  | D. Monitoring and controlling phase | 0
9 | 2 | A project manager has just taken over a project that is in its project phase. The previous project manager did not perform any risk management activities, and the project team will begin executing the project work in two days. What should the project manager do first? | A. Continue the project as already planned | 0
|  |  | B. Identify the project risks | 0
|  |  | C. Create a risk management plan | 1 | No matter where in the life cycle a project is at, risk management should begin with the creation of the risk management plan. Jumping immediately to the identification of risks means not properly assessing them. Remember that the risk management plan also outlines how risk management will be carried out, as well as definitions of risk probability and impact, and the tolerance levels of the project stakeholder.
|  |  | D. Develop a risk response plan | 0
10 | 2 | Which of the following inputs can reveal the risk attitudes of the organization? | A. Enterprise environmental factors | 1 | enterprise environmental factors reveal the organization’s risk attitudes through the organization’s actions and policies.
|  |  | B. Organizational process assets | 0
|  |  | C. Project scope statement | 0
|  |  | D. Project management plan | 0
1 | 3 | The process of risk identification has just been completed. At this point, the risk register contains all of the following EXCEPT: | A. List of identified risks | 0
|  |  | B. List of responses | 1 | Although the list of potential risk responses are documented as risks are identified (when available), the risk register does not contain the actual risk responses at this point.
|  |  | C. Root causes of risk | 0
|  |  | D. Updated risk categories | 0
2 | 3 | Which of the following statements BEST describes documentation reviews? | A. A review of the project management plan to determine the approach to risk identification. | 0
|  |  | B. A review of lessons learned to determine if they have been documented. | 0
|  |  | C. A review of the project risks to determine if they are complete and consistent. | 0
|  |  | D. A review of the project plans to determine if they are complete and consistent. | 1 | Documentation reviews is responsible for looking at project plans and documents and performing a structured review to determine whether they are accurate, in line with the project requirements and complete. Option D best summarizes this description.
3 | 3 | All of the following are characteristics of the Delphi technique EXCEPT: | A. Feedback is collected in one cycle | 1 | The Delphi technique involves risk experts who receive a questionnaire from a facilitator about important risks. The facilitator receives the feedback from experts, summarizes the information, and resends the questionnaire after summarizing the responses until consensus is reached. The feedback from experts are taken anonymously to remove the group bias. Based on this, option A is an inaccurate statement. Options B, C and D are accurate characteristics.
|  |  | B. Responses are anonymous | 0
|  |  | C. It reduces bias in the data | 0
|  |  | D. It is repeated until consensus is reached | 0
4 | 3 | While identifying risks, the project manager asks the risk manager to show how one particular element of the project can influence the other elements. The purpose is to uncover uncertainty within potential paths. What tool should the risk manager use? | A. Cause and effect diagram | 0
|  |  | B. Systems flow chart | 0
|  |  | C. influence diagram | 1 | The project manager is looking for information that can be provided using an influence diagram. Influence diagrams display this information by showing causal influences, time ordering of events, and other relationships among variables and outcomes.
|  |  | D. Ishikawa diagram | 0
5 | 3 | Which of the following diagrams is used to identify the potential causes of risk? | A. Fishbone diagram | 1 | Potential causes of risk can be shown using a cause and effect diagram. This type of diagram is also known as an Ishikawa diagram, after its founder, and a fishbone diagram, named for how it looks.
|  |  | B. Influence diagram | 0
|  |  | C. Scatter diagram | 0
|  |  | D. Histogram | 0
6 | 3 | In gathering information to identify risks, the risk management team is likely to use all of the following EXCEPT: | A. Brainstorming | 0
|  |  | B. SWOT Analysis | 0
|  |  | C. Root cause identification | 0
|  |  | D. Risk urgency assessment | 1 | Risk urgency assessment is a technique used when performing qualitative risk analysis. Options A, B, and C are information gathering techniques used in performing risk identification.
7 | 3 | As a project manager, you are told to identify strengths and weaknesses of your project. Which tool would you use? | A. Hold a brainstorming session | 0
|  |  | B. Perform SWOT Analysis | 1 | Assessing an organization’s opportunities and threats, which are presented as factors occurring outside of the organization (such as the shifting economy), can be evaluated in terms of the organization’s strengths and weaknesses. This is done through the SWOT analysis technique.
|  |  | C. Conduct interviews with risk experts | 0
|  |  | D. Obtain feedback through the Delphi technique | 0
8 | 3 | A project manager facilitated a meeting where the 30 participants were divided into groups of five with the goal of building a comprehensive list of risks. At the end of the meeting, each group went through their list, and each risk was discussed until one major list was generated. What technique did the project manager use? | A. Interviews | 0
|  |  | B. Brainstorming | 1 | In this scenario, the project manager is holding a brainstorming session. Dividing the participants into smaller groups and then meeting to discuss the results of the smaller sessions is known as the nominal group technique. A brainstorming session may use the nominal group technique, or be held as one large session. The purpose of a brainstorming session is to generate a comprehensive list of risks.
|  |  | C. Checklist analysis | 0
|  |  | D. Delphi technique | 0
9 | 3 | All of the following statements are true EXCEPT: | A. The risk register is created within the Risk Identification process | 0
|  |  | B. The risk register contains information about the project risks | 0
|  |  | C. Potential risk responses are documented as risks are identified | 0
|  |  | D. The status of risks are documented as part of risk identification | 1 | The status of risks are added and updated within the risk register as part of monitoring and controlling activities, which occurs after the project work has been executed. This would therefore not occur during the Risk Identification process.
10 | 3 | The project manager has identified risks, obtained feedback from risk experts, checked the project assumptions, and performed a review of the project plans. What might the project manager do next? | A. Perform assumptions analysis | 0
|  |  | B. Hold brainstorming sessions | 0
|  |  | C. Perform checklist analysis | 1 | Based on the scenario provided, the project manager has already carried through options A, B and D. that leaves option C, checklist analysis, as the only potential from the options provided. Checklist analysis involves the creation of risk checklists with the purpose of making sure that all items within the project have been considered for risks.
|  |  | D. Hold interviewing sessions | 0
1 | 4 | A project manager with a limited budget set aside for risk analysis purposes is likely to do what? | a. Perform qualitative and quantitative risk analysis | 0
|  |  | b. Skip both qualitative and quantitative risk analysis | 0
|  |  | c. Perform quantitative risk analysis only | 0
|  |  | d. Perform qualitative risk analysis only | 1 | Qualitative risk analysis is considered to be a rapid and cost-effective way of establishing priorities for risk response planning. With this being the case, a limited budget may only allow for qualitative risk analysis. Quantitative risk analysis, on the other hand, tends to take a greater number of resources and time to perform. An experienced risk manager may carry out quantitative risk analysis directly after identifying risks (note that the question does not specify whether the project manager is experienced at performing risk analysis). Option A would not be feasible, since the assessment of risks is important to developing a response.
2 | 4 | A project manager is in the process of performing qualitative risk analysis. To date, all risks have been assessed, the quality of the data analyzed, and risks requiring an urgent response have been documented. The project manager is now getting ready to perform quantitative risk analysis. What has the project manager forgotten to do? | a. Assign an overall risk rating | 1 | Assigning an overall risk rating helps to prioritize risks and therefore focus on those risks that have the greatest impact on the project objectives. During risk assessment, a risk rating is typically assigned on a probability level and an impact level. This is commonly followed by the use of a risk probability and impact matrix, which combines probability and impact to assign an overall risk rating.
|  |  | b. Determine the risk probability and impact | 0
|  |  | c. Perform risk urgency assessment | 0
|  |  | d. Perform risk data quality assessment | 0
3 | 4 | Which of the following plays an important role in risk assessment? | a. Risk urgency levels | 0
|  |  | b. Stakeholder risk tolerance | 1 | All of the options listed play a role in risk assessment. The questions ask that you identify one of the options that is considered ‘important”. Technically, all the options are important, but which should be at the forefront? The correct choice is stakeholder risk tolerance, since this drive how risks will be assessed.
|  |  | c. The level of technology being produced | 0
|  |  | d. The type of organizational structure | 0
4 | 4 | You are the project manager of a software development project. You are responsible for leading the risk management efforts, and have just finished identifying risks. What comes next? | a. Prioritizing the identified risks | 1 | Notice that the first three options represent a process. Risk identification is followed by qualitative risk analysis, which involves the prioritization of risks (option A). Option D is incorrect, since this would have been done during the first risk management process.
|  |  | b. Numerically analyzing risks | 0
|  |  | c. Developing a risk response plan | 0
|  |  | d. Defining risk probability and impact | 0
5 | 4 | A risk manager is performing qualitative risk analysis. Out of the 42 risks identified, 30 have been prioritized, 5 have been labeled as urgent, and the remaining risks were deemed to be low priority. Which of the following BEST describes what the risk manager will most likely do with the low priority risks: | a. Document them within the project management plan | 0
|  |  | b. Document them within the risk register | 0
|  |  | c. Place them on a watchlist | 1 | Low priority lists are placed on a Watchlist, which is monitored throughout the life of the project. Option B is also good choice, since the Watchlist is documented within the risk register, but option C offers a more specific and therefore the BEST option.
|  |  | d. Nothing, since they are low priority | 0
6 | 4 | All of the following are tools and techniques of then Qualitative Risk Analysis process EXCEPT: | a. Risk categorization | 0
|  |  | b. Risk urgency assessment | 0
|  |  | c. Risk data quality assessment | 0
|  |  | d. Assumptions Analysis | 1 | Assumptions analysis is a part of the Risk Identification process. Be sure study which tools and techniques belong to which process.
7 | 4 | A time sensitive risk is considered to be what? | a. A risk that exhibits a high rating | 0
|  |  | b. A risk that requires a near-term response | 1 | A time sensitive risks has some form of time restriction for implementing and D may appear like attractive responses, but they are not always the case and are based on the specifics of a risk.
|  |  | c. A risk that exhibits no symptoms or warnings signs | 0
|  |  | d. A risk that would result in project failure | 0
8 | 4 | All of the following are updates made to the risk register as a result of performing qualitative risk analysis EXCEPT: | a. Risks requiring additional analysis and response | 0
|  |  | b. Prioritized list of risks | 0
|  |  | c. Probabilistic analysis of the project | 1 | Option C is an update made to the risk register as a result of performing quantitative risk analysis.
|  |  | d. Watchlist | 0
9 | 4 | You are the project manager of a project responsible for the development of a new housing community. Currently, you are in the process of performing risk analysis. Five days before a key planning meeting, the project sponsor asks that you report on which areas of the project have been most affected by risk. What should you do? | a. Perform risk categorization | 1 | Risk categorization involves grouping risks by source. This is an effective technique for determining the areas of a project that are most affected by risk.
|  |  | b. Perform risk urgency assessment | 0
|  |  | c. Conduct a documentation review | 0
|  |  | d. Conduct checklist analysis | 0
10 | 4 | Conducting risk probability and impact assessment is not possible without: | a. The Watchlist | 0
|  |  | b. a risk manager present | 0
|  |  | c. the risk probability and impact matrix | 0
|  |  | d. definitions of risk probability and impact | 1 | Option A is incorrect, since the creation of a Watchlist results from performing risk probability and impact assessment; option B is not accurate, since it is not required that the facilitator of risk assessment meetings be a risk manager (although they should have experienced in risk assessment); the risk probability and impact matrix is not used in risk assessment, making option C incorrect. This leaves option D, definitions of risk probability and impact. Without the definitions properly documented, risk assessment is not accurate or effective. Definitions of risk probability and impact are normally documented during the creation of the risk management plan.
1 | 5 | If a risk has a 75% chance of occurring, and an impact of $42,000, what is the expected monetary value of the risk? | A. $73,500 | 0
|  |  | B. $31,500 | 1 | In order to calculate expected monetary value, multiply the impact by the probability. In this case, you would multiple $42,000 by 75% to get $31,500 (B).
|  |  | C. $35,700 | 0
|  |  | D. $10,500 | 0
2 | 5 | You are the project manager of a software development project. Currently, you are analyzing risks on a quantitative level. Which of the following would you use to validate the data and techniques used to carry out this process? | A. Interviews | 0
|  |  | B. Sensitivity | 0
|  |  | C. Expert judgment | 1 | Validating the data and techniques can be done through expert judgment. This includes information and feedback from subject matter experts that are internal or external to the organization.
|  |  | D. Modeling and simulation | 0
3 | 5 | A risk manager will most likely display the results of sensitivity analysis using: | A. a cause and effect diagram | 0
|  |  | B. a tornado diagrams | 1 | Tornado diagrams are commonly used to display sensitivity analysis results. A tornado diagram compares the importance of variables that have a high degree of uncertainty to more stable variables.
|  |  | C. an influence diagrams | 0
|  |  | D. a histogram | 0
4 | 5 | A project manager is in the process of calculating the three-point estimate of an activity’s completion date for risk analysis purposes. Based on information provided during an interview, he uses the following estimates: a most likely estimate of 36, a pessimistic estimate of 67, and an optimistic estimate of 20. What is the result of the calculation? | A. 38.5 | 1 | the formula for calculating a three-point estimate is: [(0 + 4(ML) + P) / 6], where “O” represents the optimistic estimate, “ML” represents the most likely estimate, and “P” represents the pessimistic estimate. When plugging in the numbers, you get the following calculation: [(20 + 4(36) + 67) / 6]. Work out the problem and you result in an estimate of 38.5.
|  |  | B. 36 | 0
|  |  | C. 41 | 0
|  |  | D. 20.5 | 0
5 | 5 | Which of the following statement BEST describes modeling and simulation? | A. It is a technique performed many times by a computer program. | 0
|  |  | B. It is used for cost and schedule risks. | 0
|  |  | C. It randomizes values from a probability distribution function. | 0
|  |  | D. It translates uncertainties of a project into the potential impacts on project objectives | 1 | You’ll notice that all of the options relate to modeling and simulation, with several providing characteristics of the technique. Option D is the only one that provides more of a description as opposed to a description of one of its characteristics.
6 | 5 | A project management team is faced with a decision to make under uncertain circumstances. In order to work through the best scenario, what technique can the team use? | A. Probability distribution | 0
|  |  | B. Interview | 0
|  |  | C. Monte Carlo | 0
|  |  | D. Decision tree | 1 | A technique that is used to choose between uncertain paths is decision tree analysis. EMV is used to solve the decision tree and make a choice.
7 | 5 | A project manager has been asked to calculate the standard deviation of an activity for risk analysis purposes. Based on information provided during an interview, he uses the following estimates: a most likely estimate of 36, a pessimistic estimate of 67, and an optimistic estimate of 20. What is the result of the calculation? | A. 2.33 | 0
|  |  | B. 1.83 | 0
|  |  | C. 5.17 | 0
|  |  | D. 7.83 | 1 | Similar to question #4, you need to know a formula to answer the question correctly. The formula calculating standard deviation is [(P – O) / 6]. When plugging in the numbers, you get the following calculation: [(67 – 20)] / 6. Work out the problem and you result in a standard deviation of 7.83.
8 | 5 | Three-point estimates are commonly displayed using: | A. Uniform distributions | 0
|  |  | B. Lognormal distributions | 0
|  |  | C. Triangular distributions | 1 | Triangular and beta distributions are the most common used probability distribution types, according to the PMBOK® Guides.
|  |  | D. Beta distributions | 0
9 | 5 | A project manager is in the process of numerically analyzing risks. While performing quantitative risk analysis, she uses the sensitivity analysis technique. What can she hope to gain from the results of the analysis? | A. To determine which risks have the most potential impact on the project. | 1 | Sensitivity analysis is used to determine which risks have the highest impact on the project objectives, making A the correct choice. This technique looks at the effects that a project element has on other project elements held at their baseline values.
|  |  | B. To determine which risks have a higher probability of occurring. | 0
|  |  | C. To determine which risks should be placed on the Watchlist. | 0
|  |  | D. To determine which risks should be placed on the Watchlist. | 0
10 | 5 | All of the following are inputs of the Quantitative Risk Analysis process EXCEPT: | A. Organizational process assets | 0
|  |  | B. Enterprise environmental factors | 1 | For the exam, you will need to know the inputs, tools and techniques and outputs of each risk management process. Option B is the only one that is not an input to the Quantitative Risk Analysis process. In addition to A, C, and D, this process also has the following inputs: risk register and the project management plan.
|  |  | C. Project scope statement | 0
|  |  | D. Risk management plan | 0
1 | 6 | During project execution, a risk response plan is implemented after predefined conditions that have been documented occur, signaling the need for a response. A contingency plan proves ineffective. What should the risk management team do NEXT? | A. Implement a contingency strategy | 0
|  |  | B. Develop a new response | 0
|  |  | C. Implement a fallback plan | 1 | A fallback plan is a planned response that is implemented after all other planned responses prove ineffective. It is similar to a “plan B”.
|  |  | D. Accept the result | 0
2 | 6 | Days before the project work is to be executed, the risk management team discovers a positive risk that could decrease the project costs by 20%. Making this risk occur would increase the current costs by 5%. It would be in the project’s best interest to: | A. share the risk | 0
|  |  | B. exploit the risk | 1 | The savings of making the risk occur far exceeds the cost. Therefore, it might be in the best interest of the project to make sure the risk happens, which would be the “exploit” strategy.
|  |  | C. mitigate the risk | 0
|  |  | D. accept the risk | 0
3 | 6 | The area where critical project equipment is housed has experienced a spike in theft over the past year. Two months into the project, a critical piece of production equipment is stolen, setting the organization back by $200,000 as a result of replacement costs. What should have been done to prepare for the risk? | A. Planned for a reserve to cover replacement costs | 0
|  |  | B. Installed a security camera | 0
|  |  | C. Moved the equipment to a safer location | 0
|  |  | D. Purchased insurance | 1 | In this case, it would have been a better option to transfer the risk to other organization, which makes D the best option. Option B seems attractive, but it reduces the probability of the theft by an unknown amount.
4 | 6 | Altering the project schedule to deal with a negative risk is an example of which risk response strategy? | A. Avoid | 1 | Altering a plan to eliminate a risk is the “avoid” strategy. If eliminating a risk is not possible or feasible, then we move into the mitigate strategy.
|  |  | B. Transfer | 0
|  |  | C. Mitigate | 0
|  |  | D. Exploit | 0
5 | 6 | Altering the project schedule to deal with a positive risk is an example of which risk response strategy? | A. Avoid | 0
|  |  | B. Mitigate | 0
|  |  | C. Enhance | 0
|  |  | D. Exploit | 1 | Exploiting a risk is similar to the “avoid” strategy. What is being done in both cases is to eliminate the uncertainty of a risk. In this case, we are eliminating the uncertainty that the risk will occur by altering the project schedule, since it is a positive risk.
6 | 6 | All of the following are used as inputs in developing a risk response EXCEPT: | A. Documented potential responses | 0
|  |  | B. The contingency strategy | 1 | Option B is not a possible choice, since a contingency strategy is used as a technique during the development of a risk response, and not an input.
|  |  | C. The risk rating | 0
|  |  | D. Root causes of risk | 0
7 | 6 | In response to a negative risk that could not be eliminated, the project manager has decided to recommend reducing the impact. What strategy is this? | A. Avoid | 0
|  |  | B. Exploit | 0
|  |  | C. Mitigate | 1 | Reducing the impact and/ or probability in response to a negative risk is an example of mitigating it.
|  |  | D. Passive acceptance | 0
8 | 6 | Which of the following is an example of mitigating a risk? | A. Building a prototype | 1 | As we saw with #7, mitigating a risk involves reducing the probability and impact that a risk will occur. Building a prototype is an example of this. Option B is an example of transfer; and option D is an example of avoid.
|  |  | B. Purchasing insurance | 0
|  |  | C. Developing a partnership | 0
|  |  | D. Altering the project schedule | 0
9 | 6 | Which of the following is an example of exploiting a risk? | A. Setting aside a reserve fund to manage the risk | 0
|  |  | B. Forming a joint venture with a production company | 0
|  |  | C. Running additional tests to increase the probability and impact | 0
|  |  | D. Adding a senior resource to complete an activity faster | 1 | Adding a senior resource is often used as a way of completing an activity faster or increasing the quality, allowing for a condensing of the schedule. It typically involves higher costs as well.
10 | 6 | A new risk was discovered one month after the execution of the project work had begun. After assessing and analyzing the risk, it was determined that responding to the risk would be more costly than allowing the risk to follow its own course. A reserve was set aside to deal with the result of the risk, if it were to occur. What strategy was used? | A. Mitigate | 0
|  |  | B. Passive acceptance | 0
|  |  | C. Active acceptance | 1 | An analysis of the risk was made, and an active acceptance was made.
|  |  | D. Avoid | 0
1 | 7_8 | As the project work is executed, an issue emerges as a result of a risk that had gone undetected. What type of response should the risk management team implement? | A. A secondary plan | 0
|  |  | B. A contingency plan | 0
|  |  | C. A fallback plan | 0
|  |  | D. A workaround | 1 | A workaround is an unplanned response to a negative risk that has occurred. Notice a key difference between a workaround and all other responses: it is unplanned.
2 | 7_8 | When a new risk is identified while carrying out Risk Monitoring and Control activities, what should the risk management team do FIRST? | A. Develop a risk response | 0
|  |  | B. Audit the risk | 0
|  |  | C. Assess the risk | 1 | When a new risk is identified, it should be taken through the risk management processes. Of the options presented, assessing the risk would come first, making C the best choice.
|  |  | D. Analyze the risk | 0
3 | 7_8 | As part of conducting risk monitoring and control activities, what should be done with the Watchlist? | A. The risk should be numerically analyzed | 0
|  |  | B. The risks should be monitored for a change in status | 1 | Risk on the Watchlist should be monitored regularly to determine whether a change of status has occurred. It wouldn’t be feasible to analyze low priority risks on a numerical level or develop a response to low-priority risks. Doing nothing about a risk until it becomes an issue should be strategy that is planned.
|  |  | C. A response should be developed for each risk | 0
|  |  | D. Nothing, unless one of the risks becomes an issue | 0
4 | 7_8 | The project manager is concerned about potential risk occurring as a result of performance deviations from the baseline. What should the project manager do? | A. Perform risk audits | 0
|  |  | B. Conduct technical performance measurement | 0
|  |  | C. Perform variance and trend analysis | 1 | Variance and trend analysis forecasts potential cost and/or schedule deviations of the project at completion to uncover potential risks. It also looks for deviations of performance in comparison to the performance baselines.
|  |  | D. Reassess all risks | 0
5 | 7_8 | Which of the following is an output of performing risk monitoring and control activities? | A. The development of contingency plans | 0
|  |  | B. Recommended preventive actions | 1 | Options A and C are updates resulting out of Risk Response Planning. While changes are requested as a result of the Risk Monitoring and Control process, they are not implemented until approval from the integrated change control board is received, making option D incorrect. This leaves option B, recommended preventive actions.
|  |  | C. Risk-related contractual agreements | 0
|  |  | D. Changes to the project management plan | 0
6 | 7_8 | The project management team is in the process of monitoring risks. Of the 70 risks identified, half received an immediate response, and ten have been realized. What should the project management team do to ensure that enough funds remain to deal with the remaining risks, should they occur? | A. Implement a workaround | 0
|  |  | B. Conduct a risk audit | 0
|  |  | C. Perform variance and trend analysis | 0
|  |  | D. Perform reserve analysis | 1 | A reserve fund is typically set aside to deal with risks. Reserves analysis involves the comparison of remaining risk to the remaining reserve. This allows the project management team to determine whether enough reserve remains to deal with risks.
7 | 7_8 | All of the following statements are true EXCEPT: | A. A risk management should be discussed during status meetings at least quarterly | 1 | Status meetings should be used as a means of discussing risk management on a regular basis (if not during every status meeting). Discussing risk management on a quarterly basis with the project team is not effective, making option A the best choice.
|  |  | B. New risks can be identified while performing risk monitoring and control activities | 0
|  |  | C. Risk reassessment should be scheduled regularly as part of risk monitoring and control | 0
|  |  | D. Risk audits are concerned with the effectiveness of the risk management processes | 0
8 | 7_8 | In closing out risk management activities, a project manager archives the risk register, updates the project management plan, and archives the revised risk management templates. What has the project manager forgotten to do? | A. Hold a closure meeting | 0
|  |  | B. Conduct risk reassessment | 0
|  |  | C. Archive lessons learned | 1 | Archiving of lessons learned is an important part of risk management closure and project closure overall.
|  |  | D. Hold a risk review | 0
9 | 7_8 | Which of the following BEST describes the purpose of technical performance measurement? | A. Comparing actual technical accomplishments to planned accomplishments. | 1 | Comparing actual technical accomplishments to planned accomplishments.
|  |  | B. Creating a baseline of technical performance based on the amount of risk. | 0
|  |  | C. Measuring the amount of technical performance achieved. | 0
|  |  | D. Documenting technical performance as risks are monitored. | 0
10 | 7_8 | Which of the following techniques uses earned value analysis to determine whether any deviations exist? | A. Option Risk audits | 0
|  |  | B. Variance and trend analysis | 1 | VETA is a part of Earned Value analysis.
|  |  | C. Technical performance measurement | 0
|  |  | D. Reserve analysis | 0